## Slide 1: Health Promotion Implementation: Planning health promotion interventions
Tulani Francis L. Matenga
Department of Health Promotion and Education

## Slide 2: Development Management Projects: Cycles, Elements and Logic
This section aims to discuss the concept of a project. It looks at the project cycle, its elements and most important the logic. It further looks at the planning processes in development management.

## Slide 3: The project concept
Defining a project is difficult. Numerous scholars and social commentators defined projects differently.
Thus, there is no universally applicable definition of a project. The Project Management Book of Knowledge defines a project as a ‘temporary endeavor undertaken to create a unique product or a service.

## Slide 4: The project concept Cont’d
‘Temporary’ since every project has a definite end and ‘unique’ in that the product is different in from all similar services.
A project is ‘an endeavor in which human material and financial resources are organized in a novel way to undertake a unique scope of work of a given specification within a constraint of cost and time so as to deliver beneficial change defined as Quantitative and Qualitative objectives (Rodney Turner, 1990).

## Slide 5: The project concept Cont’d
A project is a clearly scheduled group of actions carried out to attain specific objectives implemented by an organization established or appointed particularly for it. It is a task that has specific purpose or goal or a unique task directed at causing change.
In other words, projects are tools used to implement health promotion plans. In achieving HPE plans, we can look at projects to be coordinated sets of activities and tasks designed to achieve given stated objectives.
Some of the key features of an HPE project include having start time and end time (life cycle); associated with a cash flow; essentially unique activities and non-repetitive; having a single point of responsibility and many more others.

## Slide 6: The project concept Cont’d
Project features in brief
A project has a unique purpose
A project is temporary
A project requires resources, often from various sources
A project involves a certain level of uncertainty
A project should have a primary sponsor or customers

## Slide 7: Project cycle
Broadly, there exist two ways of looking at lifecycles that work in conjunction with one another throughout the course of every project.
  First, a project lifecycle describes the tasks that must be completed in order to produce a product or service e.g a project lifecycle followed to build a house.
  On the other hand, what they call project management lifecycle defines how to manage a project.
An understanding of these two concepts is important as one of project managers’ challenges is to comprehend how to align the specific project lifecycle with the project management lifecycle.

## Slide 8: Project cycle Cont’d
While different and diverse and unique, projects tend to follow a set of defined steps from project identification to project end. That is, projects consists of various activities whose relations are sequentially defined by scope, schedule, budget and ultimate performance.
Thus, development projects are usually performed in stages forming a logical cycle.
Basically project cycle might involve assessment and planning, implementation, monitoring, review, and evaluation.

## Slide 9: Project cycle Cont’d
Project Identification/Assessment
Project Design
Project Appraisal
Project Implementation
Project Evaluation & Learning

## Slide 10: Project cycle Cont’d
    Elements of the project cycle
      i. Project need identification
        This is the conceptualisation and initial stage.
        Development project needs identification starts by examining [with different stakeholders] existing social projects and priority areas.
        It is this identified problem need (s) that translates into project goals, purposes, outputs and activities.
ii. Design
  Once the need is identifies, project preparation and analysis follows. The scope of the project will have to be determined (coverage of the project).
  Good project designs should have objectives that are:
    clearly and realistically stated;
    reflect, from the point of view of the beneficiaries, the desired improvement;
    allow main results, resources and implementation approach to be derived from them;

## Slide 11: Project cycle Cont’d
    specific and measurable indicators are attached for each objective in order to enable quantitative and qualitative monitoring of the project
    The time-schedule is clear, realistic, covers its whole lifetime
    The project has a clear and efficient management structure and organisation
    The monitoring and reporting system should enable effective project management and incorporate feedback to work planning
    Resources are specified and sufficient in relation to the objectives and expected outcomes.
    Based on these the budget can be prepared

## Slide 12: Project cycle Cont’d
      iii. Development Project appraisal
  Development project appraisal aims at facilitating selection from among existing alternatives. Feasibility studies are significant in determining project alternatives that are viable.
  These are appraised in order to select one or more that appear to maximise development project objectives.
  Thus, the project alternative selected should aim at maximising identified objectives.
  The purpose of the pre-feasibility and feasibility analyses is to identify and eliminate from consideration alternatives that for some reasons are not feasible or fail to maximise project objectives.
  As a decision process, feasibility might look at each identified alternatives in terms of: the need to be met; project objectives; resources available; environmental conditions to be met; practicality of the solution; social-economic implications of the project; and acceptability (stakeholders)

## Slide 13: Project cycle Cont’d
iv. Implementation
  Once the project alternative that maximises the objectives is selected, its implementation and operationalization follows. Thus, after you have carefully planned your project, you will be ready to start the project implementation phase;
  Implementation phase involves putting the project plan into action. It will have to be according to plans developed earlier in the previous project phases;
  It is important to remember that monitoring is done at this stage feeding into continuous learning needs;
  It’s here that the project manager will coordinate and direct project resources to meet the objectives of the project plan. The project implementation phase aim at producing specific deliverables.
  The word ‘deliverable’ means anything your project delivers.

## Slide 14: Project cycle Cont’d
      v. Evaluation and Learning
  This is the final phase in the development project cycle
  Gives an organisation feedback on whether a project is achieving what it set out to achieve. It enables us to prove to our communities, funding bodies and other interested parties that we did what we said we were going to do (accountability)
  Help us to learn (what worked and what didn’t? how can I repeat the successes and minimise the mistakes? Is the project sustainable? (Improvement)
  Contribute to our evidence base around what works (Knowledge).
  Learning function. Evaluation is not limited to completed projects. It can also be an important tool for management in on-going projects. Evaluation might be undertaken when the project is in trouble as the first step in the re-planning effort.

## Slide 15: Three key development project principles
1. Problem-based approach
  Projects do not emerge from without. They are not haphazard.
  Projects are planned processes. And since they demand financial outlay or resource outlay problem based approach argue projects emerge to address real needs and problems.
  Projects are problem driven/aimed at solving existing problems in the social world.
2. Stakeholder-orientation approach
  Projects involve co-operation with the local beneficiaries and stakeholders from early preparation and planning phases.
  Successful development projects are driven by carefully isolated stakeholders that all have a bearing on the project outcome.
3. Objective-oriented approach
  Projects focus on desired improvements and achievements during the planning and implementation. This specific objectives provide the not only the scope but also the focus of your intervention.
  In any case, projects are driven by the desired improvements the project aims or objectives

## Slide 16: Programs Vs Projects
What then is the Difference?
  Although sometimes used interchangeably, programs differ from projects.
  In order to understand this, it is important to distinguish between projects and programs and projects
Project
  Projects look at the execution and implementation processes. As pointed earlier projects are temporary undertakings to produce a unique product, service or result.
  Projects are a combination of related activities DESIRED GOAL
  Most people think of a project as producing something tangible, however the deliverable of a project could simply be an answer to a question.
  A number of projects may form a development program

## Slide 17: Programs Vs Projects
Program
A program consists of a series of related and possibly interdependent projects that meet an overarching objective;
The Project Management Book of Knowledge defines program as ‘group of related projects managed in a coordinated way to obtain benefits and control not available from managing them individually’;
Thus a program is different from a project. It is in fact a collection of projects. Sometimes projects are complimentary and help the program achieve its overall objectives;
Programs have larger scope than projects and typically run at higher levels in organisations;
The specific deliverables of each project would be defined when each project starts and should align with the strategic goals of the program. The program is usually long.

## Slide 18: Differences between Projects and Programs in brief
Projects | Programs
Stems from an assemblage of related tasks/activities [that might feed into a program] | Stems from an assemblage of related projects
Rollup reporting involves aggregating tasks/activity performance | Rollup reporting involves aggregating project performance
Focused on ‘outputs’ and deliverables. These are results of a process. If it can be touches; can be seen then it is probably an output. | Focused on ‘outcomes’; benefits and achievements. These outcomes are things than can be grouped and analysed for trends.
Typically smaller in size and intended impacts | Typically larger in size and intended impacts
Managed by project managers | Managed by program managers

## Slide 19: Linking project inputs, activities, outputs, outcomes and impacts
There are a number of terminologies that are confused if not misunderstood in development management. A good understanding these terminologies not only ensures that appropriate indicators are identified, but also that they are effectively measured.

## Slide 21: Development Project Inputs
Inputs are NOT synonymous with activities. Inputs, in simple terms, are the material and non-material, financial and non-financial resources that we use in the project to implement it.
For example, in any project, inputs would include things like human resource (personnel), finances in the form of money, machinery such a vehicles, and equipment such as public address systems among others.
The significance of inputs ensure that it is possible to deliver the intended results of a project.
Without inputs the project cannot deliver that it intends to attain.

## Slide 22: Development project Activities
Activities on the other hand are actions associated with delivering project goals. In other words, they are what the personnel/employees do in order to achieve the aims of the project.
These need careful planning from the outset. In any case, these will have to be linked intricately to the objectives.

## Slide 23: Development project Outputs
These are the first level of results associated with a project. Outputs are the direct immediate term results associated with a project.
In other words, they are usually what the project has achieved in the short term. An easy way to think about outputs is to quantify the project activities that have a direct link on the project goal.
For example, project outputs in a HIV and AIDS project would be: the number of community awareness meetings that were done, the number of condom dispensers installed, number of HIV and AIDS infected persons referred for ARTs among others.

## Slide 24: Development project Outcome
This is the second level of results associated with a project and refers to the medium term consequences of the project. Outcomes usually relate to the project goal or aim.
For example, in a safe water project, an outcome would be “the percentage of households that are using chlorinated drinking water”. Another outcome could be “the percentage of children suffering from diarrhoea.”
Nevertheless, an important point to note is that, outcomes should clearly link to project goals.

## Slide 25: Development project Impact
Most often than not, it is very difficult to ascertain the exclusive impact of a project since several other projects, not similar in nature can lead to the same impact.
An example of an impact would be reduced poverty rates, reduced child mortality rates among others.
In the case of the Safe Water project, an increase in the number of households using treated water would directly impact on fewer cases of people suffering from diarrhoea, meaning that there will be a reduced number of lost man-hours.
This has a direct impact on poverty reduction. Also, the number of children suffering from diarrhoea may reduce, meaning that the cases of child deaths are reduced.

## Slide 26
Thank you